## Hand Sign Lang Detection WBS
Work Breakdown Structure |  | Hand Sign Language Detection
Project Start | Fri,Nov 24,2023
Levels | WBS | Task Description | Status | Notes
1 | 1 | Project Planning | Completed
2 | 1.1 | Relevant Research papers Walkthrough | Completed
2 | 1.2 | Scope of work | Completed
3 | 1.2.1 | Identify Risk / Challenges | Completed
1 | 1.2.2 | Project Resources - Hardware /Sofware | Completed
2 | 1.2.2.1 | Create Project Outline | Completed
4 | 1.2.2.2 | Create WBS | Completed
4 | 1.2.2.3 | Walkthrough with Supervisor | Completed
2 | 1.3 | Create Powerpoint for the BITS Outline VIVA | Completed
1 | 2 | Project Design , Data Preprocessing /Preparation | In Progress
2 | 2.1 | Architecture Design creation | Completed
3 | 2.1.1 | Data Capture Methodology | Completed
3 | 2.1.2 | Data Preparation | Completed
4 | 2.1.3 | Document Creation | In Progress
1 | 3 | Model Evaluation | In Progress
2 | 3.1 | Model Selection | Completed
3 | 3.2 | Model Training using Few Hand Sign Language | Completed
4 | 3.3 | Model Evaluation | Completed
5 | 3.4 | Hand Sign detection validation using Image | Completed
6 | 3.5 | Mid Sem Progress status with Supervisor | Completed
6 | 3.5 | Mid Sem Report Review | In Progress
1 | 4 | Model Testing | Not Started
2 | 4.1 | Hand Sign Detection validation using Video | Not Started
3 | 4.2 | Real time Hand Sign Detection Evaluation | Not Started
4 | 4.3 | Post Evaluation, Testing Real Time Hand Sign Detection | Not Started
5 | 4.4 | Performance Validation of Real time hand sign detection vs Image | Not Started
6 | 4.5 | Final Sem Report Preparation | Not Started
1 | 5 | Future Scope of work - Outside Project Dissertation | Not Started
2 | 5.1 | Integrating with the Web Apps | Not Started
3 | 5.2 | Testing Web Apps in Cloud | Not Started
4 | 5.3 | Feasibiltiy of Real time Detection using Web cam | Not Started
5 | 5.4 | Enhancing the App to show the continous sentence post detection | Not Started
6 | 5.5 | Testing the Web Apps using Mobile Application and Performance validation | Not Started